## Implementation plan matrix
Objective aligned to Strategic doc (NST, V2050, SSP) | Outcome | Indicator | Units | Baseline (latest) | End period target (2028/29) | 2024/25 |  | 2025/26 |  |  | 2026/27 |  |  | 2027/28 |  | 2028/29 |  |  | Responsible Institutions (Which institutions hold the responsibility to do this and to be budgeted)
[6 empty] | Key interventions/projects/programmes | [11 empty] | Total cost
SPORTS
4.3. High-end, eco-friendly, and diversified tourism | Outcome 1. Increased revenues generated from sports | Amount of revenues generated from sports | Frw | non | 30000000000 | 1000000000 |  | 5000000000 |  |  | 13000000000 |  |  | 21000000000 |  | 30000000000 |  |  | RAB
|  | Number of jobs created in the sports sector (list by discipline in the SSP) | Number | 2500 for 2023-2024 | 3190 | 2625 |  | 2756 |  |  | 2894 |  |  | 3038 |  | 3190
|  | Number of youths participating in organized sports programs (by discipline) | Number | 599 for 2023-2024 | 37000 | 7400 |  | 14800 |  |  | 22200 |  |  | 29600 |  | 37000
|  | Number of certified coaches and trainers (by discipline) | Number | 200 (Base TBC) | 5200 | 1200 |  | 2200 |  |  | 3200 |  |  | 4200 |  | 5200
|  | Number of certified sports administrators | Number | 20 (Base TBC) | 270 |  | 70 |  | 120 |  |  | 170 |  |  | 220 |  | 270
|  | Number of athletes competing at international levels (By discipline) | Number | 300 (Base TBC) | 550 | 350 |  |  | 400 |  |  | 450 |  |  | 500 |  | 550
|  | Number of new or renovated sports facilities (both public and private (in schools, churches, etc..) | Number | 37 sports facilities renovated 2023-2024 | 540 Handbal 3 footbal 3 basketbal 3 volleyball 3 cycling 3 Athletic 3 ( 3 center per Discipline and per District) 360 district centers (Means 2 facilities per center at the District level ) 132 Regional centers 34 National level | Isonga program 108 at primary level, 72 at the Secondary level 27 at regional centers |  | Isonga program 108 at primary level, 72 at the Secondary level 27 at regional centers |  |  | Isonga program 108 at primary level, 72 at the Secondary level 27 at regional centers 17 at National level |  | 108 | Isonga program 108 at primary level, 72 at the Secondary level 27 at regional centers 17 at National level |  | Isonga program 108 at primary level, 72 at the Secondary level 27 at regional centers |  |  | AFD and MINISPORTS
|  | Capacity utilization rate of major stadiums (Amahoro, Arena,HUYE, Nyamirambo, and those built in secondary districts) | Number of events | Amaho 5 events' BK Arena | 20 | 20 |  | 20 |  |  | 20 |  |  | 20
|  | Investment in sports infrastructure (public and private) meeting international standards | numbers | Amaho stadium Cricket Stadium' Tennis courts at IPRC Kicukiro, Kigali Golf Course, BK Arena indoor stadium, Kigali Pele stadium | 5 | 1 |  | 1 |  |  | 1 |  |  | 1 |  | 1
| Ioutcome 2. ncreased sports participation boosts Rwandans' health and wellness, while stronger sports organizations fuel economic growth. | Participation rates in grassroots sports programs | Number | car free day 2 a month CoK and Secondary cities, Sports for all at Sector level twice a month | 4 | 4 |  | 4 |  |  | 4 |  | 4 | 4
|  | Number of sports facilities at community level availed | Number | 53 playgrounds 2023-2024 | 500 | 100 |  | 100 |  |  | 100 |  |  | 100 |  | 100
CULTURE
6.4. National Unity, Resilience, culture and values | Outcome 2. Rwandan culture, values and norms embedded in daily lives of Rwandans . | Proportion of Rwandans with knoweldge of Rwandan culture its values and norms | % | TBD | .+10% | Target to be TBD Develop guidelines and content on Itorero program at Village and school levels; - Conduct a Barometer on the knowledge of Rwandans on their culture and values; -Organise National Heroes celebration 2025; .- Conduct a research on the role of Itorero in strengthening ubutore culture |  | Target to be TBD .- Monitor the operationalisation of Itorero at Village level and primary and secondary schools; - Establish Itorero in public and none public institutions; -Mobilise specific groups on cultural values and norms ( Artists, …..); .-Organise National Heroes celebration 2026; .-Conduct a reserch on Heroes and outstanding Achivers; - Organise Umuganura 2025; -Develop Nkumba Ubutore Center phase 3 developed; - Publish findings on the role of Itorero and Urugerero in strengthening Ubutore Culture |  |  | Target to be TBD on knowledge on Rwandan culture and values .+2.5% on impact level of Rwandan culture on national unity - Monitor the operationalisation of Itorero at Village level, in schools and institutions; - Establish Itorero in Rwandan Community Abroad; .- Conduct Mobilisation on Cultural values among specific groups (Journalists,Parents..); .-Organise National Heroes celebration 2027; .-Conduct a reserch on Heroes and outstanding Achivers; .- Organise Umuganura 2026 |  |  | Target to be TBD on knowledge on Rwandan culture and values ..+2.5% on impact level of Rwandan Cultre on national unity - Monitor the operationalisation of Itorero at Village level , schools , institutions and RCA; .-Mobilisation on Cultural values among specific groups (Parents, youth,..); .- Conduct a research on Heroes and outstanding Achivers; .-Organise Umuganura 2027,. .-Organise Nationa Heroes celebration 2028 - National Heroes Mausoleum phase 2 developed |  | .+10% ( On knowledge of cultural values) & +5% on Impact level of Rwandan culture on national unity .-Monitor the operationalisation of Itorero at Village level, in schools , institutions and RCA; .-Conduct a Barometer on the knowledge of Rwandans on their culture and values; .- Mobilisation on Cultural values is conducted among specific groups (Parents, youth,..); .- Conduct a reserch on Heroes and outstanding Achivers; .- Organise Umuganura 2028; .- Organise National Heroes celebration 2029. |  | MINUBUMWE RCHA | MINUBUMWE RCHA
|  | Impact level of Rwandan culture, its values and norms on national unity | Qualitative | TBD | .+5%
|  | Percentage use of Ikinyarwanda in different institutions in accordance with langauge policies and regulations | % | 49% of private institutions | .+20% | .- Conduct media based program on correct use of Ikinyarwanda; - Research on Ikinyarwanda terminologies in ICT Sector |  | .-Disseminate in public and none public institutions guidelines on protection of Ikinyarwanda .- Conduct media based awareness on corrrect use of Ikinyarwanda; .- Moblisation and capacity reinforcment of specific groups on correct use of ikinyarwanda (Artists,…); - Research on Ikinyarwanda terminologies in ICT Sector |  |  | .- Conduct media based awareness on corrrect use of Ikinayrwanda ; -Mobilisation on Correct use of Ikinyarwanda among groups groups ( Journalists ) - Research on correct use of Ikinyarwanda within the Rwandan population ; Research on Ikinyarwanda terminologies in Health Sector |  |  | .10% - Media based awareness on corrrect use of Ikinayrwanda ; - A research on use of Ikinyarwanda in institutions in accordance with language policies and regulations - Research on Ikinyarwanda terminologies in Health sector |  | .10% .- Media based awareness on corrrect use of Ikinayrwanda ; -A research on use of Ikinyarwanda in institutions in accordance with language policies and regulations; |  | MINUBUMWE RCHA | RCHA
| Outcome 4. Rwandan cultural heritage preserved and promoted | Number of visitors that visited Rwandan cultural heritage facilities | No. | 257855 | 486782 | 283640 - Develop an approved study on Gikoba Open Air Museum |  | 296533 - Finalise National Liberation Museum pahse 3; -Develop Gikoba Open Air Museum in collaboration with RDB; - Rehabiliate Queen Gicanda House; - Develop digital mapping of 5 cultural heritage sites. |  |  | 310426 Develop digital mapping of 10 cultural heritage sites |  |  | 386782 - Develop Kings Palace Museum Phase 2; - Develop digital mapping of 10 cultural heritage sites, - Develop and adopt Legal frame works governing Archives services and book management |  | 486782 - Develop digital mapping of 5 cultural heritage sites |  | MINUBUMWE RCHA | RCHA
4.11 Creation of sustainable and decent jobs | Outcome 5: Cultural and Creative Industries strenghened towardsJob creation and income generations | % of contribution of CCI to other services in GDP | % | 5% ( 2023) | 6% | 5.2% |  | 5.4% |  | 5.6% |  |  | 5.8% |  |  | 6% |  |  | Lead: MOYA Stakeholders: RDB,MINICOM,PSF
|  | Number of People employed in CCI | No. | 9,452 (2023) | 62760 | 10,452 1. Scale up Arts Rwanda Ubuhanzi and Arts connekt 2. Attracting and hosting international arts events for exchange purpose and knowledge transfer 3.Establish a framework to use the existing public and private infrastructures (Arena, KCEV, Kigali Cultural Village/Rebero, stadiums, Petit stade, etc) for Artists. 4. Mobilize and attract the private sector to invest in creative industries as an emerging sector with potential to generate income and job creation. 5. Develop a legal framework related to CCIs development |  | 11,502 1. Scale up Arts Rwanda Ubuhanzi and Arts connekt 2. Attracting and hosting international arts events for exchange purpose and knowledge transfer 3.Establish a framework to use the existing public and private infrastructures (Arena, KCEV, Kigali Cultural Village/Rebero, stadiums, Petit stade, etc) for Artists. 4. Mobilize and attract the private sector to invest in creative industries as an emerging sector with potential to generate income and job creation. 5. Develop a legal framework related to CCIs development |  | 12,552 1. Scale up Arts Rwanda Ubuhanzi and Arts connekt 2. Attracting and hosting international arts events for exchange purpose and knowledge transfer 3. Mobilize and attract the private sector to invest in creative industries as an emerging sector with potential to generate income and job creation. |  |  | 13,602 1. Scale up Arts Rwanda Ubuhanzi and Arts connekt 2. Attracting and hosting international arts events for exchange purpose and knowledge transfer 3. Mobilize and attract the private sector to invest in creative industries as an emerging sector with potential to generate income and job creation. |  |  | 14,652 1. Scale up Arts Rwanda Ubuhanzi and Arts connekt 2. Attracting and hosting international arts events for exchange purpose and knowledge transfer 3. Mobilize and attract the private sector to invest in creative industries as an emerging sector with potential to generate income and job creation. |  |  | Lead: MOYA Stakeholders: RDB,MINICOM,PSF

## Jobs to Revenue Ratio (hidden)
Company | Employees | Revenue | Ratio
Bakhresa Grain Milling | 100 | 21500000 | 4.6512e-06
Pembe Flour Mills | 40 | 28500000 | 1.4035e-06
Minimex | 80 | 4500000 | 1.7778e-05
ICM Rwanda | 160 | 13000000 | 1.2308e-05
Coffee Business Center (CBC) | 26 | 13500000 | 1.9259e-06
Kivu Arabic Coffee Company(KCC) | 17 | 3500000 | 4.8571e-06
RWACOF | 45 | 13500000 | 3.3333e-06
Rwanda Trading Company(RTC) | 75 | 8500000 | 8.8235e-06
RWASHOSCCO | 40 | 3500000 | 1.1429e-05
Rwanda Mountain Tea(RMT) | 155 | 15500000 | 1e-05
Sorwathe(Societe Rwandaise de The) | 521 | 7500000 | 6.9467e-05
Kabuye Sugar Works | 550 | 10500000 | 5.2381e-05
Premier Tobacco Company(PTC) | 129 | 2500000 | 5.16e-05
Shekina Enterprises | 41 | 1000000 | 4.1e-05
Horizon Sopyrwa(Societe de Pyrethre au Rwanda) | 72 | 6500000 | 1.1077e-05
Sorwatom | 32 | 1000000 | 3.2e-05
Bralirwa | 528 | 132500000 | 3.9849e-06
Brasserie de Milles Collines | 78 | 10500000 | 7.4286e-06
Inyange Industries | 195 | 10500000 | 1.8571e-05
Laiterie de Nyanza | 60 | 1000000 | 6e-05
Enterprise Urwibutso(Sina Gerard) | 200 | 3500000 | 5.7143e-05
Ameki Color | 380 | 6500000 | 5.8462e-05
Cimerwa | 262 | 20000000 | 1.31e-05
Kigali Cement Company | 42 | 1500000 | 2.8e-05
Ruliba Clays | 210 | 1500000 | 0.00014
Safintra | 40 | 11500000 | 3.4783e-06
Simaco/Afrifoam | 85 | 2500000 | 3.4e-05
SteelRwa | 240 | 8500000 | 2.8235e-05
Tolirwa(Toliere Industrielle du Rwanda) | 110 | 12500000 | 8.8e-06
Ufametal | 23 | 8500000 | 2.7059e-06
Uprotur | 85 | 2500000 | 3.4e-05
Anik industries | 30 | 1500000 | 2e-05
Aqua-San | 25 | 1500000 | 1.6667e-05
Kigali Steel & Aluminum Works | 20 | 1500000 | 1.3333e-05
Manumetal | 57 | 2500000 | 2.28e-05
Mutara Entreprises | 85 | 3500000 | 2.4286e-05
Roto Ltd | 60 | 3500000 | 1.7143e-05
Rwanda Foam | 80 | 3500000 | 2.2857e-05
Societe Rwandaise de Chaussures(SRC) | 100 | 2500000 | 4e-05
Suku Paper Works/Safari Center | 50 | 5500000 | 9.0909e-06
Sulfo Industries | 700 | 13500000 | 5.1852e-05
Trust Industries | 50 | 1500000 | 3.3333e-05
Utexrwa | 600 | 5500000 | 0.00010909